# Project Plan: Whisper Speech-to-Text Module

Prepared by: Franz Kingstein Nesakumar

# Objective

To develop and integrate a speech recognition module using OpenAI's Whisper API that accepts audio input (.wav/.mp3), transcribes it to text, and sends the result to the backend via REST API or WebSocket.

# Task Breakdown and Descriptions

| Task | Description |
| --- | --- |
| Development | Implement core functionality: audio input, transcription using Whisper API, multi-turn dialogue support, and data return via REST/WebSocket. |
| Testing & Debugging | Unit testing with various audio samples, simulate noisy inputs, and correct functional errors. |
| Team Evaluation | Share the module with team for code review, usability testing, and feedback. |
| Final Overall Testing | Conduct integrated testing with backend, evaluate full transcription and response loop. |
| Documentation & Cleanup | Write developer guide, API usage summary, and clean up the codebase for maintainability. |
| Buffer Time | Reserve time for unforeseen issues, bug fixes, or last-minute improvements. |

# Time Estimation (in Days)

| Task | Duration (Days) |
| --- | --- |
| Development | 4 days |
| Testing & Debugging | 2 days |
| Team Evaluation | 2 days |
| Final Overall Testing | 2 days |
| Documentation & Cleanup | 1 day |
| Buffer Time | 1 day |
| Total Estimated Time | 12 days |

# Task Dependencies

- Development must be completed before Testing & Debugging.
- Team Evaluation follows after the module is tested.
- Final Testing can only start post team evaluation.
- Documentation comes after all technical validation is done.
- Buffer time is used at the very end.

# Schedule (Starting from Day 1)

| Day | Task | Notes |
| --- | --- | --- |
| 1 | Development | Setup, API integration, audio input |
| 2 | Development | Format handling, Whisper logic |
| 3 | Development | Multi-turn support, response output |
| 4 | Development | REST/WebSocket integration, cleanup |
| 5 | Testing & Debugging | Unit tests, short/long clips |
| 6 | Testing & Debugging | Simulate errors, edge case handling |
| 7 | Team Evaluation | Code review, feedback |
| 8 | Team Evaluation | Fixes based on review |
| 9 | Final Overall Testing | Backend integration tests |
| 10 | Final Overall Testing | Full flow verification |
| 11 | Documentation & Cleanup | Write docs, finalize API details |
| 12 | Buffer Time | Fixes, polish, backup |

# Gantt Chart Overview

Day:         1   2   3   4   5   6   7   8   9  10  11  12
-------------------------------------------------------
Development: ███ ███ ███ ███
Testing:                 ███ ███
Evaluation:                   ███ ███
Final Testing:                     ███ ███
Docs & Cleanup:                           ███
Buffer:                                      ███